## Sheet1
Project Title: Price Tracker
Name: Mohammad Navid Nayyem
Student ID: 172014003
Task | Start Date | End Date | Duration
Feasibility Analysis Report | 2020-11-09 | 2020-11-12 | 4
Data collection about various e-commerce sites. Develop ER diagram | 2020-11-13 | 2020-11-22 | 10
Implementation of database system using MySQL. Connection with Django | 2020-11-23 | 2020-12-05 | 13
Basic extension development, connection of extension with database | 2020-12-06 | 2020-12-15 | 10
Website development, price of particular products showing | 2020-12-16 | 2020-12-31 | 16
Price comparison of different sites in extension | 2021-01-01 | 2020-01-06 | 6
Complete Extension interface. Showing price history of all products | 2021-01-07 | 2020-01-13 | 7